## Sheet1
Task Name | Duration | Start | Finish | IST Start | IST Finish | Predecessors | Notes | Resource Names | Hosted
BI-Connect / myBusiness Go-Live Cut-Over Plan | 100.63 days? | Mon 10/1/18 8:00 AM | Sat 11/3/18 9:00 PM | NA | NA
Resources for Go-Live | 0.1 days | Mon 10/1/18 8:00 AM | Mon 10/1/18 8:48 AM | NA | NA |  | Identify Network (firewalls, ports, DNS), DBA's, System Admins
Sanofi | 0.1 days | Mon 10/1/18 8:00 AM | Mon 10/1/18 8:48 AM | Mon 10/1/18 5:30 PM | Mon 10/1/18 6:18 PM |  | CRQ needed (William Joel, Accenture, etc) | William Joel,Accenture,Sandep,Sanjay | Sanofi
BI | 0.1 days | Mon 10/1/18 8:00 AM | Mon 10/1/18 8:48 AM | Mon 10/1/18 5:30 PM | Mon 10/1/18 6:18 PM |  | Coordinate with BI INF (David Maris,etc) | David Maris | BI
DataPipe | 0.1 days | Mon 10/1/18 8:00 AM | Mon 10/1/18 8:48 AM | Mon 10/1/18 5:30 PM | Mon 10/1/18 6:18 PM |  | Ticket with Datapipe |  | Datapipe
Pre-Go Live Activites | 85.63 days? | Mon 10/1/18 8:00 AM | Mon 10/29/18 9:00 PM | NA | NA |  |  |  | BI
URL's and Sites | 1 day | Mon 10/1/18 8:00 AM | Mon 10/1/18 4:00 PM | NA | NA |  |  |  | BI
Identify all URL's and DNS entries that need to be changed | 1 day | Fri 10/19/18 9:00 AM | Fri 10/19/18 5:00 PM | Fri 10/19/18 6:30 PM | Sat 10/20/18 2:30 AM |  |  |  | BI
Identify any sites that will have to remain active in Sanofi | 1 day | Fri 10/19/18 9:00 AM | Fri 10/19/18 5:00 PM | Fri 10/19/18 6:30 PM | Sat 10/20/18 2:30 AM | 8FS-1 day |  |  | BI
Identify all files that need to be moved from the servers (not databases) | 1 day? | Fri 10/19/18 9:00 AM | Fri 10/19/18 5:00 PM | Fri 10/19/18 6:30 PM | Sat 10/20/18 2:30 AM | 8FS-1 day
Production Databases | 8.63 days? | Fri 10/26/18 12:00 AM | Sun 10/28/18 9:00 PM | NA | NA
Schedule last full backup of all servers | 2 days | Fri 10/26/18 12:00 AM | Fri 10/26/18 4:00 PM | Fri 10/26/18 9:30 AM | Sat 10/27/18 1:30 AM |  |  |  | Sanofi
Full Database Backups | 3 days | Fri 10/26/18 9:00 PM | Sat 10/27/18 9:00 PM | NA | NA
BI-Connect (Portalmart, etc) | 3 days | Fri 10/26/18 9:00 PM | Sat 10/27/18 9:00 PM | Sat 10/27/18 6:30 AM | Sun 10/28/18 6:30 AM | 12 |  |  | Sanofi
myBusiness | 3 days | Fri 10/26/18 9:00 PM | Sat 10/27/18 9:00 PM | Sat 10/27/18 6:30 AM | Sun 10/28/18 6:30 AM | 12 |  |  | Sanofi
Restore Full Backup of Prodcution Databases | 3 days? | Sat 10/27/18 9:00 PM | Sun 10/28/18 9:00 PM | NA | NA | 14,15 |  |  | BI
BI-Connect (Portalmart, etc) | 24 hrs | Sat 10/27/18 9:00 PM | Sun 10/28/18 9:00 PM | Sun 10/28/18 6:30 AM | Mon 10/29/18 6:30 AM
myBusiness | 24 hrs | Sat 10/27/18 9:00 PM | Sun 10/28/18 9:00 PM | Sun 10/28/18 6:30 AM | Mon 10/29/18 6:30 AM |  | will need to estimate the backup.
Charles submit ticket to perform restore. | 1 day? | Sat 10/27/18 9:00 PM | Sun 10/28/18 5:00 AM | Sun 10/28/18 6:30 AM | Sun 10/28/18 2:30 PM |  | Will need this for Monday
Load Balancer | 10 days | Fri 10/26/18 1:00 PM | Mon 10/29/18 9:00 PM | NA | NA
Verify Load Balancer is in place and working properly | 10 days | Fri 10/26/18 1:00 PM | Mon 10/29/18 9:00 PM | Fri 10/26/18 10:30 PM | Tue 10/30/18 6:30 AM | 11FS-7 days
Network Montoring | 1 day | Fri 10/26/18 1:00 PM | Fri 10/26/18 9:00 PM | NA | NA
Verify Network monitoring is in place and active | 1 day | Fri 10/26/18 1:00 PM | Fri 10/26/18 9:00 PM | Fri 10/26/18 10:30 PM | Sat 10/27/18 6:30 AM | 11FS-7 days
Go-Live Cut Over Activities | 3 days? | Fri 10/19/18 8:00 PM | Sat 10/20/18 8:00 PM | NA | NA
Shutdown Process | 0.25 days | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | NA | NA
Shutdown BI-Connect legacy & myBusiness | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 6FS+10 days | Charles \ Satish M - Stop all sites on am-usa38-ecomp1
Merial DMZ Domain Controller | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | ?
Production Load Balancer | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | ?
Production Sharepoint Servers | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | Charles \ Satish M - Stop all sites on both servers
Shutdown myBusiness Legacy | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | Charles \ Satish M \ Chandra - Stop all sites on am-usa38-ecomp1 ¦ disable the TIBCO jobs
Datapipe - WhiteList to prevent internet access | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | Not sure - TCS
Change DNS entires to point to Datapipe | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | Geoff
Change Ordipat DNS changes from Sanofi to Datapipe | 2 hrs | Fri 11/2/18 8:00 PM | Fri 11/2/18 10:00 PM | Sat 11/3/18 5:30 AM | Sat 11/3/18 7:30 AM | 26FS-2 hrs | Charles ¦ Geoff
Production Databases - Backup | 0.63 days | Fri 11/2/18 10:00 PM | Sat 11/3/18 3:00 AM | NA | NA | 25
BI-Connect - Perform Differential Backup | 5 hrs | Fri 11/2/18 10:00 PM | Sat 11/3/18 3:00 AM | Sat 11/3/18 7:30 AM | Sat 11/3/18 12:30 PM |  | Alan to coordinate with Naresh ¦ Ticket should already be open |  | Sanofi
myBusiness - Perform Differential Backup | 5 hrs | Fri 11/2/18 10:00 PM | Sat 11/3/18 3:00 AM | Sat 11/3/18 7:30 AM | Sat 11/3/18 12:30 PM |  | Alan to coordinate with Naresh ¦ Ticket should already be open |  | Sanofi
Production Databases - Restore | 0.63 days | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | NA | NA | 34 | This time includes moving the databases from Sanofi to BI
BI-Connect - Perform Differential Backup | 5 hrs | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | Sat 11/3/18 12:30 PM | Sat 11/3/18 5:30 PM |  | Naresh and Sanofi |  | Datapipe
myBusiness - Perform Differential Backup | 5 hrs | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | Sat 11/3/18 12:30 PM | Sat 11/3/18 5:30 PM |  | Charles to coordinate with Naresh and Accenture |  | Datapipe
Will need to coordinate the restores. | 5 hrs | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | Sat 11/3/18 12:30 PM | Sat 11/3/18 5:30 PM
Miscellaneous Tables and Folders | 5 hrs | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | Sat 11/3/18 12:30 PM | Sat 11/3/18 5:30 PM |  | Rajesh and Nanadkumar to coordinate
Move Identfied tables and folders from WFE & web05/06 servers to datapipe from Sanofi | 5 hrs | Sat 11/3/18 3:00 AM | Sat 11/3/18 8:00 AM | Sat 11/3/18 12:30 PM | Sat 11/3/18 5:30 PM |  | Rajesh and Nanadkumar to coordinate
Apply Last changes to portals | 0.5 days | Fri 11/2/18 10:00 PM | Sat 11/3/18 2:00 AM | NA | NA | 25
BI-Connect | 0.5 days | Fri 11/2/18 10:00 PM | Sat 11/3/18 2:00 AM | NA | NA
Move All Code to New Production Environment | 2 hrs | Fri 11/2/18 10:00 PM | Sat 11/3/18 12:00 AM | Sat 11/3/18 7:30 AM | Sat 11/3/18 9:30 AM |  | move this to 10/26 - Confirn with Nandkumar and Satish M
Verify and Signoff on New Production Code Environments | 2 hrs | Sat 11/3/18 12:00 AM | Sat 11/3/18 2:00 AM | Sat 11/3/18 9:30 AM | Sat 11/3/18 11:30 AM | 45 | All developers and PMs
myBusiness | 0.5 days | Fri 11/2/18 10:00 PM | Sat 11/3/18 2:00 AM | NA | NA |  | Need networking resources for go-live, Firewall changes, DBA's
Move last minute code changes to New Production Environment | 2 hrs | Fri 11/2/18 10:00 PM | Sat 11/3/18 12:00 AM | Sat 11/3/18 7:30 AM | Sat 11/3/18 9:30 AM |  | Seeshil and Bharath to confirm ¦ Monday 29th
Verify and Signoff on New Production Code Environments | 2 hrs | Sat 11/3/18 12:00 AM | Sat 11/3/18 2:00 AM | Sat 11/3/18 9:30 AM | Sat 11/3/18 11:30 AM | 48 | All developers and PMs
Interfaces - Activate for Production | 0.13 days | Sat 11/3/18 8:00 AM | Sat 11/3/18 9:00 AM | NA | NA | 37,43
Corticon | 1 hr | Sat 11/3/18 8:00 AM | Sat 11/3/18 9:00 AM | Sat 11/3/18 5:30 PM | Sat 11/3/18 6:30 PM |  | Savitha to confirm ¦ Alan to send email when we are ready to start testing
Tibco Jobs | 1 hr | Sat 11/3/18 8:00 AM | Sat 11/3/18 9:00 AM | Sat 11/3/18 5:30 PM | Sat 11/3/18 6:30 PM |  | Chandra ¦ Mehul or provided backups ¦ Alan to confirm when we are ready to start testing
GDW jobs | 1 hr | Sat 11/3/18 8:00 AM | Sat 11/3/18 9:00 AM | Sat 11/3/18 5:30 PM | Sat 11/3/18 6:30 PM |  | Rajesh ¦ Ramana ¦ Vignesh ¦ Dharam ¦ Alan to confirm when we are ready to start testing
SSIS & SSRS packages | 1 hr | Sat 11/3/18 8:00 AM | Sat 11/3/18 9:00 AM | Sat 11/3/18 5:30 PM | Sat 11/3/18 6:30 PM |  | Rajesh and Dharam
Run jobs to catchup | 0.13 days | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | NA | NA | 50
Corticon | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Savitha to confirm ¦ Alan to send email when we are ready to start testing
Tibco Jobs | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Chandra ¦ Mehul or provided backups ¦ Alan to confirm when we are ready to start testing
GDW jobs | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Rajesh ¦ Ramana ¦ Vignesh ¦ Dharam ¦ Alan to confirm when we are ready to start testing
SSIS & SSRS packages | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Rajesh and Dharam
Validate configuration changes | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Rajesh¦ Nandkumar ¦ Satish to make any DB changes, and validate
Portalmart loading data/interfaces SSIS packages to run | 1 hr | Sat 11/3/18 9:00 AM | Sat 11/3/18 10:00 AM | Sat 11/3/18 6:30 PM | Sat 11/3/18 7:30 PM |  | Rajesh
IT Readiness Assessment | 0.38 days | Sat 11/3/18 10:00 AM | Sat 11/3/18 1:00 PM | NA | NA | 50,55
Validate All Applications are Live and Available - IT Unit Test | 2 hrs | Sat 11/3/18 10:00 AM | Sat 11/3/18 12:00 PM | Sat 11/3/18 7:30 PM | Sat 11/3/18 9:30 PM |  | Satish - will need to do some configure changes in the database,
Go/No-Go Checkpoint | 1 hr | Sat 11/3/18 12:00 PM | Sat 11/3/18 1:00 PM | Sat 11/3/18 9:30 PM | Sat 11/3/18 10:30 PM | 63 | Team
Firewalls - Open to Internet | 0.13 days | Sat 11/3/18 1:00 PM | Sat 11/3/18 2:00 PM | NA | NA | 62
Remove Whitelist to fully open production to all Users | 1 hr | Sat 11/3/18 1:00 PM | Sat 11/3/18 2:00 PM | Sat 11/3/18 10:30 PM | Sat 11/3/18 11:30 PM
Business Readiness Assessment | 0.75 days | Sat 11/3/18 2:00 PM | Sat 11/3/18 8:00 PM | NA | NA |  | Todd
Business Production UAT | 3 hrs | Sat 11/3/18 2:00 PM | Sat 11/3/18 5:00 PM | Sat 11/3/18 11:30 PM | Sun 11/4/18 2:30 AM | 65
Business Go-Live Sign Off | 1 hr | Sat 11/3/18 5:00 PM | Sat 11/3/18 6:00 PM | Sun 11/4/18 2:30 AM | Sun 11/4/18 3:30 AM | 68
Remove whitelist to fully open production to all Users | 2 hrs | Sat 11/3/18 6:00 PM | Sat 11/3/18 8:00 PM | Sun 11/4/18 3:30 AM | Sun 11/4/18 5:30 AM | 69 | Time change this weekend. Extra hour
Release Systems for Go-Live | 1 hr | Sat 11/3/18 8:00 PM | Sat 11/3/18 9:00 PM | Sun 11/4/18 5:30 AM | Sun 11/4/18 6:30 AM | 67

## Sheet3
Application Name | User Name | Role
MRP | mmperregaux@snet.net
Previcox Survey Program | mobilevet@ymail.com
Client Connection Plus | malibuvetclinic@gmail.com
Advance | gulfgateanimalhospital@yahoo.com
MyBusiness | paulpullen@myvetsmeds.com | Administrator
MyBusiness | jclark@svp.vet | ShiptoManager
MyBusiness | diana@warriordogrescue.com | Buyer
MyBusiness | 207079 | Customer Care Rep
MyBusiness | Jay.Hrencher@Merial.com | Sales Rep
eCouponing | luszoo4@yahoo.com
eCouponing VIP | jayasankar.javangula@merial.com
Premier | chrissytarr12@gmail.com
Sales Agent Portal | courtney.carter@merial.com
MCP | Kirsten.deveau@merial.com
Max | maxadmin@gmail.com